# Verkada Camera Migration & Configuration Execution Playbook

Migration from TRENDnet PoE to UniFi USW-Pro-Max-48-PoE (VLAN 60) – Technical Reference for Network Engineers

# 1. Technical Specifications & Prerequisites

## 1.1 PoE Requirements

- Standard Models (CD42-E, CD52-E): 802.3af (7–12W)

- Advanced Models (CD62-E, CM62-E, Dome IR): 802.3at (15–25W)

- Profile Setting: Auto-negotiate (af/at); budget 15W/port (avg.)

## 1.2 Bandwidth Allocation (Verkada 2025 Specs)

- Idle: 20–50 Kbps/camera (heartbeat/metadata)

- Motion (720p): 150–400 Kbps (burst)

- Live View (720p): 1–2 Mbps (sustained)

- Live View (4K): 3–6 Mbps (if applicable)

- Firmware Updates: 5–10 Mbps/camera (stagger: 3 cams/15 min, cap 30 Mbps aggregate)

## 1.3 Cloud Connectivity Requirements

- HTTPS: TCP 443 (to *.control.verkada.com, *.vstream.verkada.com, *.vauth.verkada.com, api.verkada.com, firmware.verkada.com)

- DNS: UDP/TCP 53

- NTP: UDP 123 (time.control.verkada.com, pool.ntp.org)

- STUN (WebRTC): UDP 3478

- ICMP: Type 3 Code 4 (Path MTU Discovery)

- Local Streaming (RTSP): TCP 554 (LAN-only for Protect integration)

## 1.4 Network Settings

- MTU: 1500 (standard; do not enable jumbo frames)

- DSCP Marking: AF41 (DSCP 34) for QoS

- NTP Hierarchy: time.control.verkada.com → pool.ntp.org

## 1.5 Cat5e Status

- Verified for PoE/GbE at <100m

- Q1 2026: Fluke certification to TIA-568-B

- Monitor >90m runs for link flaps

# 2. Phase 1: Pre-Migration Preparation (1.5 Hours)

## 2.1 Verkada Inventory Audit

- Login to command.verkada.com

- Navigate: Settings → Organization → Devices

- Confirm: Auto-Adopt: Enabled (Settings → Organization → Network)

- Note Organization ID for support

- Local Streaming: Enable if using RTSP to VLAN 99 (Settings → Organization → Streaming)

- Export device CSV: Serial, MAC, Model, Firmware, Location, Status

- Check firmware uniformity (if >2 minor versions diff, schedule pre-migration update; allow 24–48h staggered)

- Identify all 802.3at models for PoE planning

- Create Camera Inventory Spreadsheet:

- Cam #SerialMACModelPoE ClassLocationUSW PortRTSP UserNotes

- 1V123ABC00:11:22:33:44:55CD42-Eaf (9W)Front Entrance26cam01_rtspDome

-	2V456DEF00:22:33:44:55:66CD62-Eat (18W)Parking Lot27cam02_rtspIR heater

## 2.2 Physical Preparation

- Cable Labeling (30 min):

- Label each camera cable at TRENDnet port (e.g., "Cam1-Front → USW-26")

- Label new USW ports 26–40 correspondingly

- Photo-document current TRENDnet port assignments (for rollback)

TRENDnet Resale Prep:

Photograph serial numbers and note model numbers (TPE-T50g, TPE-TG44g)

Plan for factory reset post-migration (hold reset 10s powered)

## 2.3 Staged Production Validation (No Lab Camera)

Critical: Use a phased production rollout due to lack of lab camera.

- Pilot Migration (2–3 non-critical cams): Select hallway or similar, migrate during off-hours.

- Document baseline metrics for later comparison.

Pilot Success Criteria (all must pass before bulk migration):

- Cloud status “Online” within 2 min

- PoE draw matches spec (±2W)

- NTP sync (within 1s of system clock)

- RTSP stream accessible from VLAN 99 (if used)

- Motion triggers recording in Command

If any FAIL:

- Document with screenshots (Command)

- Unplug pilot cams from USW, reconnect to TRENDnet

- Verify cameras come “Online” again

- Capture Wireshark on VLAN 60 during failure

- Open Verkada support ticket (support@verkada.com) with logs

- Halt bulk migration until resolved

# 3. Phase 2: Production Network Configuration (45 Minutes)

## 3.1 Camera Port Profile (UniFi)

- UniFi Console: Settings → Profiles → Switch Port Profile → Create New

| Setting | Value | Notes |
| --- | --- | --- |
| Name | Verkada-Cams-VLAN60 |  |
| Native VLAN | 60 (untagged) | Access mode |
| PoE Mode | Auto | Negotiates af/at |
| PoE Max Power | 25.5W | 802.3at ceiling |
| Storm Control | Broadcast 5%, Multicast 5% | Flood prevention |
| STP | Enabled, Edge Port | Fast convergence |
| LLDP | Enabled | PoE negotiation |
| Isolation | Disabled | Cloud access required |
| Priority | 4 (AF41/DSCP 34) | QoS marking |
| Apply to Ports | 26–40 | 15 ports for 12–15 cams + headroom |

- Verify: Console → Devices → USW-Pro-Max-48-PoE → Ports → View PoE StatusExpect: PoE Standard (af/at), Power Draw: 7–25W (model dependent)

## 3.2 VLAN 60 Network Settings

- UniFi Console: Settings → Networks → Create New

- Name: Verkada-Cameras

- VLAN ID: 60

- Gateway/Subnet: 10.60.0.1/26

- DHCP: Server; Range 10.60.0.10–10.60.0.62; Lease: 86400s (24h)

- DNS: 10.60.0.1 (fwd to 8.8.8.8)

- NTP: Enabled; Servers: time.control.verkada.com, pool.ntp.org

- MTU: 1500

- mDNS: Off

- IGMP Snooping: Off

- IPv6: Off

- ICMP: Allow Type 3 Code 4 outbound (firewall rule)

## 3.3 DHCP Reservations

- Console → Networks → Verkada-Cameras → DHCP → Fixed IP

- Assign MACs to statics (.10–.25) per Inventory Spreadsheet

- Verify: Console → Clients → Filter VLAN 60 (NTP sync visible in Insights)

# 4. Phase 3: Firewall & QoS Configuration (30 Minutes)

## 4.1 Firewall Rules (VLAN 60 Traffic)

| Rule Name | Action | Source | Destination | Ports/Protocol | Notes |
| --- | --- | --- | --- | --- | --- |
| VLAN60-DNS | Accept | VLAN 60 | 10.60.0.1 or Internet | UDP/TCP 53 | DNS for *.verkada.com; log |
| VLAN60-NTP | Accept | VLAN 60 | Internet (time.*) | UDP 123 | NTP sync; log |
| VLAN60-STUN | Accept | VLAN 60 | Internet | UDP 3478 | WebRTC live view; log for troubleshooting |
| VLAN60-Cloud | Accept | VLAN 60 | Internet *.verkada.com | TCP 443 | Command/control/firmware; log hits |
| VLAN60-MTU-Discovery | Accept | VLAN 60 | Internet | ICMP Type 3 Code 4 | Path MTU |
| VLAN60-Local-Stream | Accept | VLAN 60 | VLAN 99 | TCP 554 | RTSP Protect pull; auth required |
| VLAN60-Block-Internal | Drop | VLAN 60 | Other VLANs (10/20/30/50) | All | Full segmentation; log attempts |
| VLAN60-Block-Multicast | Drop | VLAN 60 | 224.0.0.0/4 | All except 239.255.255.250 | SSDP only if needed |

## 4.2 QoS Rules

- Console → Settings → Internet → WAN → Smart Queues: Enable (420 Mbps down/up)

- Traffic Rule → Create:

- Name: Verkada-Priority

- Protocol: TCP/UDP

- Source: VLAN 60

- Destination: Internet

- Ports: 53, 123, 3478, 443

- DSCP: AF41 (34)

- Rate Limit: None (allow bursts)

Firmware Scheduling: Schedule updates during maintenance windows (10 PM – 6 AM) to avoid WAN contention with VoIP

# 5. Phase 4: Migration Execution (1.5–3 Hours, Off-Hours 1)

## 5.1 Pilot Migration (2–3 Cams – Live Validation)

- Verkada Command → Devices → Select Pilot Cams → Bulk Actions → Reprovision (forces DHCP)

- Physically unplug from TRENDnet (use labels); plug into USW ports 26–28

- Monitor:

- Auto-power-up (<30s PoE negotiation)

- Command adoption (<2min)

- Baseline: Use Wireshark on VLAN 99 host (filter: tcp.port 443/554, udp.port 123/53/3478, icmp; ip.addr == 10.60.0.0/26); log bandwidth, NTP drift

## 5.2 Bulk Migration (Remaining Cams, Post-Pilot Success)

- Command → Bulk Reprovision all

- Unplug TRENDnet branches sequentially (group by 4–6), match labels to USW 29–40

- Plug in, verify group online

- Trigger NTP sync; test motion on 20% sample

## 5.3 Testing & Validation

- Cloud: All cams “Online”; live view <3s latency

- Local: Pull RTSP from VLAN 99 (e.g., vlc rtsp://username:password@10.60.0.x:554/stream; test auth)

- Burst: Motion trigger; Wireshark <400kbps motion, NTP <1s drift

- MTU: Ping -M do -s 1472 10.60.0.1 (no frag); check ICMP logs

- PoE: Console total <180W; per-port match spec

## 5.4 Decommission TRENDnet Switches

- 100% online? Power off, remove, reset/list for resale (~$160 offset)

- Issues? Replug subset; capture Wireshark for Verkada support

# 6. Testing & Validation Checklist

- Cloud online: 100% in Command

- NTP synced: <1s drift

- Local RTSP: <5s connect w/ auth (TCP 554)

- Bandwidth: 20–50kbps idle, <400kbps motion

- DHCP/MTU: Static IPs hold; no frag errors

- PoE: Matches model spec; total <180W

# 7. Troubleshooting Guide

- Cloud Sync Fails: Check TCP 443/53; ping api.control.verkada.com, *.vstream.verkada.com; reprovision

- NTP Drift: Check UDP 123; confirm cloud/pool reachability

- PoE Insufficient: Confirm 802.3at for IR models; injector temp test if >25W draw

- Local Jitter/Frag: ICMP MTU allow; Wireshark RTSP filter; shorten Cat5e if flaps

- Firmware Spike: Stagger updates (3/15min); temp QoS bump to CS6 (48)

- STUN/WebRTC Issues: Verify UDP 3478; test live view in Command

# 8. Known Limitations

- Cold Weather: at PoE required for heaters; monitor draw in winter

- Local Only: TCP 554 LAN-bound; no cross-VLAN without explicit rules

- DoH Unsupported: Use UDP 53; no encrypted DNS

# 9. Post-Migration Optimization (Week 2)

- Rule Tune: 24h Wireshark; narrow 443 to specific Verkada endpoints as needed

- Insights Setup: Command → Alerts → Bandwidth >2Mbps; PoE >80%

- Expansion: 40% headroom (62 hosts); Q1 Cat5e cert before WiFi 6E add